## Milestone and Timeline
Milestones and Schedules
Activity | Start Date | Completion Date | Variance | March |  |  |  | April |  |  |  | May |  |  |  | June
Phase 1 |  |  |  | 1st week | 2nd week | 3rd week | 4th week | 1st week | 2nd week | 3rd Week | 4th week | 1st week | 2nd week | 3rd week | 4th week | 1st week | 2nd week | 3rd week | 4th week
Project Kick-Off | March 9, 2016 | March 9, 2016 | n/a | bar: March 2nd week
Team meetups | March 10, 2016 | March 10, 2016 | n/a | bar: March 2nd week
Project Assignment | March 11, 2016 | March 11, 2016 | n/a | bar: March 2nd week
Brainstorming | March 11, 2016 | March 11, 2016 | 1 day | bar: March 2nd week
Team Planning and Topics Research | March 11, 2016 | March 14, 2016 | 3 days | bar: March 2nd week
Tasks assignment | March 14, 2016 | March 14, 2016 | 1 day
Requirements and Design Documentation | April 1, 2016 | April 6, 2016 | 6 days | bar: April 1st week
Team Meeting | April 7, 2016 | April 7, 2016 | 1 day | bar: April 2nd week
Final Review of Requirements and Design | April 7, 2016 | April 8, 2016 | 2 days | bar: April 2nd week
Submission of Documentation | April 8, 2016 | April 8, 2016 | n/a | bar: April 2nd week
Phase 2
Feedback from Supervisor | April 11, 2016 | April 15, 2016 | 5 days | bar: April 2nd week
Meetings with Supervisor if needed | April 13, 2016 | April 13, 2016 | n/a | bar: April 2nd week
Team meeting | April 18, 2016 | April 18, 2016 | 1 day | bar: April 3rd Week
Implementation | April 19, 2016 | May 3, 2016 | 2 weeks | bar: April 3rd Week to April 4th week
Status Report | April 25, 2016 | April 29, 2016 | 5 days | bar: April 4th week
Final Review of Status Report and first Prototype | May 4, 2016 | May 5, 2016 | 2 days | bar: May 1st week
Iterations of Prototype | May 6, 2016 | May 8, 2016 | 3 days | bar: May 1st week
Final QA | May 9, 2016 | May 12, 2016 | 2 days | bar: May 2nd week
Submission of Status Report and first Prototype | May 13, 2016 | May 13, 2016 | n/a | bar: May 2nd week
Phase 3
Feedback from Supervisor | May 16, 2016 | May 20, 2016 | 5 days | bar: May 3rd week
Meetings with Supervisor if needed | May 18, 2016 | May 18, 2016 | n/a | bar: May 3rd week
Team meeting | May 19, 2016 | May 19, 2016 | 1 day | bar: May 3rd week
Final Prototype | May 24, 2016 | June 3, 2016 | 2 weeks | bar: May 4th week to June 1st week
Final Report | May 30, 2016 | June 3, 2016 | 5 days | bar: May 4th week to June 1st week
Final QA of Prototype | June 6, 2016 | June 7, 2016 | 2 days | bar: June 1st week
Final Review of Final Report | June 8, 2016 | June 8, 2016 | 1 day | bar: June 2nd week
Iterations or Revisions of Prototype and Final Report | June 9, 2016 | June 10, 2016 | 2 days | bar: June 2nd week
Submission of Prototype and Final Report | June 17, 2016 | June 17, 2016 | n/a | bar: June 3rd week
Phase 4
Team Meeting | June 21, 2016 | June 21, 2016 | 1 day | bar: June 4th week
Final Presentation | TBA | TBA | TBA

## Planned Effort per Person
Milestones and Timelines |  |  |  | Planned Effort per Person
Activity | Start Date | Completion Date | Variance | 1204827 | 1400098
Phase 1
Project Kick-Off | March 9, 2016 | March 9, 2016 | n/a | n/a | n/a
Team meetups | March 10, 2016 | March 10, 2016 | n/a | n/a | n/a
Project Assignment | March 11, 2016 | March 11, 2016 | n/a | n/a | n/a
Brainstorming | March 11, 2016 | March 11, 2016 | 1 day
Team Planning and Topics Research | March 11, 2016 | March 14, 2016 | 3 days
Tasks assignment | March 14, 2016 | March 14, 2016 | 1 day
Requirements and Design Documentation | April 1, 2016 | April 6, 2016 | 6 days
Team Meeting | April 7, 2016 | April 7, 2016 | 1 day
Final Review of Requirements and Design | April 7, 2016 | April 8, 2016 | 2 days
Submission of Documentation | April 8, 2016 | April 8, 2016 | n/a
Phase 2
Feedback from Supervisor | April 11, 2016 | April 15, 2016 | 5 days | n/a | n/a
Meetings with Supervisor if needed | April 13, 2016 | April 13, 2016 | n/a | n/a | n/a
Team meeting | April 18, 2016 | April 18, 2016 | 1 day
Implementation | April 19, 2016 | May 3, 2016 | 2 weeks
Status Report | April 25, 2016 | April 29, 2016 | 5 days
Final Review of Status Report and first Prototype | May 4, 2016 | May 5, 2016 | 2 days
Iterations of Prototype | May 6, 2016 | May 8, 2016 | 3 days
Final QA | May 9, 2016 | May 12, 2016 | 2 days
Submission of Status Report and first Prototype | May 13, 2016 | May 13, 2016 | n/a
Phase 3
Feedback from Supervisor | May 16, 2016 | May 20, 2016 | 5 days | n/a | n/a
Meetings with Supervisor if needed | May 18, 2016 | May 18, 2016 | n/a | n/a | n/a
Team meeting | May 19, 2016 | May 19, 2016 | 1 day
Final Prototype | May 24, 2016 | June 3, 2016 | 2 weeks
Final Report | May 30, 2016 | June 3, 2016 | 5 days
Final QA of Prototype | June 6, 2016 | June 7, 2016 | 2 days
Final Review of Final Report | June 8, 2016 | June 8, 2016 | 1 day
Iterations or Revisions of Prototype and Final Report | June 9, 2016 | June 10, 2016 | 2 days
Submission of Prototype and Final Report | June 17, 2016 | June 17, 2016 | n/a
Phase 4
Team Meeting | June 21, 2016 | June 21, 2016 | 1 day
Final Presentation | TBA | TBA | TBA
Legend:
| 25% |  |  | 25%
| 50% |  |  | 50%
| 75% |  |  | 75%
| 100% |  |  | 100%